## Sheet1
LeS LogiLink
Task | Status | Remark | Assigned to | Flow test
Inbound shipment grid from both Esupplier and Logilink | done |  | raviprasad
Inbound shipment grid for supplier and buyer users | done |  | raviprasad
Create delivery order from purchase order for full quantities | done |  | raviprasad
create delivery order for split quantities from purchase order lines | done |  | raviprasad
assign multiple attachments to delivery order | done | 5 files limit per DO | raviprasad
show newly created delivery orders in inbound shipment module | done |  | praddy
Remove delivery order when it is in open status | done | we are deleting delivery order and linked lines since user can recreate it. | praddy
Mast config master | pending
create new inbound shipment | pending
release inbound shipment and delivery order | pending |  | praddy